## Slide 1: Options for BESTMAP to pick up SUPREMA results
Peter Witzke, EuroCARE

## Slide 2: SUpport for Policy RElevant Modelling of Agriculture — SUPREMA
Coordination and Support Action (CSA)
30 months from 1.1.2018, 1m €
7 partners, co-ordinated by Wageningen research (WR)
  EUROCARE, Bonn
  TI, Braunschweig
  SLU, Uppsala
  IIASA, Laxenburg
  UPM, Madrid
  JRC, Seville

## Slide 3: WP1 – Challenges, needs, communication
Three stimulating stakeholder workshops but few short run impacts on project work
  Because few choice options open in 30 month project
  Possibly better options in BESTMAP. Contact: P Salamon , M Banse, TI
Exception: Roadmap
  Assessment of achievements against needs and to do list for future
Training and documentation
  Progress for all systems, but different starting points
  Potentially useful example; CAPRI (contact M Blanco, UPM)

## Slide 4: WP2 – Model enhancement and integration (1)
Targeted improvements: specific to models
Testing and versioning (stable release cycle): Very useful for CAPRI, presumably already standard in BESTMAP (given IT focus), if not: contact T Jansson, SLU
Infrastructure for comparisons
  Extension of earlier AgMIP template with more detail
  Lengthy discussions, only partial implementation
  Lesson (?): start simple – implement – improve

## Slide 5: WP2 – Model enhancement and integration (2)
IFM-CAP ⬄ CAPRI link
  Useful (and extreme) example: conversion of all farms to organic
  Related to BESTMAP even though different approach (hard linkage, no statistical upscaling). Contact: A Gocht, TI
AGMEMOD⬄ MITERRA link
  Useful example to exploit complementarity of models and top down approach (in first implementation). Contact: R Jongeneel, JP Leschen

## Slide 6: WP3 – Testing the SUPREMA model family
WP3.2 apparently overlapping with BESTMAP (medium run CAP orientation)
  Premium reforms and elements of green deal
  Diet shifts of European consumers
  Long delays to achieve realistic scenarios, but assessment potentially valuable for BESTMAP (contact R Jongeneel, WR)
Also: Baseline and long run scenario work (carbon price with different degrees of non-EU participation)
  Less focus on farm level

## Slide 7: WP4 – Coordination and management family
We had efficient coordination by F Brouwer (WR)
Project webside and cloud useful for internal communication
  But heritage is open
But : Upload of scenario results to DataM (JRC managed)
  Imposes strict format and long run visibility
  Seems to conform with BESTMAP approach
Task on governance structure useful for SUPREMA models, unclear if also for BESTMAP

## Slide 8: WP1.6: Useful headlines from road map
Remember that farm and pixel level is not all (supply chains, trade, economy), but DART-BIO is in BESTMAP
Topics related to farm level
  Neglected : fruit&vegetables, fodder
  Difficult : Adoption of technologies
    Here: Feedback to SUPREMA models like CAPRI?
Often neglected: forestry (except GLOBIOM)
Hot topics: Biodiversity, pesticides, antibiotics, animal welfare